## Overview
Microsoft
AI Centre of Excellence
Delivery RACI · MCAPS RSA
Purpose
Defines who is Responsible, Accountable, Consulted, and Informed across every phase of the AI CoE delivery motion — from Wave 1 account qualification through Cloud Accelerate Factory delivery, partner build, and renewal. Apply per Wave 1 account; tailor only the partner column when scope changes.
RACI legend
R | Responsible — does the work
A | Accountable — single owner; signs off
C | Consulted — two-way input
I | Informed — one-way update
Roles
AE | Account Executive (ATU) — owns the account commercial outcome
ATS | Account Tech Strategist (STU) — technical strategy at the account
SSP | Solution Specialist (STU) — pre-sales pursuit lead (AI / MW / BizApps)
SE | Solution Engineer (STU) — technical pre-sales, demos, POCs
PDM | Partner Development Manager (EPS) — partner lifecycle end-to-end
CSAM | Customer Success Account Manager (CSU) — orchestrates the post-sale lifecycle
CSA | Cloud Solution Architect (CSU) — Stage 1–2 technical delivery owner
Factory | Cloud Accelerate Factory PM (CSU) — F1/F2 anchor bundle delivery at $0
ISD | Industry Solutions Delivery — Microsoft-led delivery (Model B or C)
Partner | Anchor Partner — differentiated build, custom logic, managed services, run
Operating principles
• One A per row. If two leaders both think they own a step, the v-team has not been stood up — escalate to the named Area sponsor before delivery starts.
• CSA owns Stage 1–2 technical delivery. Envisioning, Frontier 5+1, surface mapping, and reference architecture sit with CSA — not partner, not SSP. Non-negotiable.
• CSAM orchestrates the lifecycle. Factory eligibility, ISD model selection, ATO Component 2 claim, adoption tracking, and hand-off accountability sit with CSAM.
• PDM owns the partner lifecycle end-to-end. Scorecard, co-sell registration, MSX hygiene — none of this falls to CSA.
• Factory absorbs predictable foundation work. F1 and F2 are accountable to the Factory PM. CSA is consulted but does not deliver the landing zone — that is the productivity gain the motion depends on.
• Partner is accountable for differentiated build and run. Custom architecture, Studio agents, M365 Copilot rollout, managed services. Anchor Partners pushing back into Stage 1–2 are escalated to PDM same-day.
Owner: Yuri Baijnath · SR CSA Manager · MCAPS RSA CSU · v1.0
Microsoft Confidential · © 2026 Microsoft Corporation

## RACI
AI CoE Delivery RACI · MCAPS RSA
# | Activity | AE | ATS | SSP | SE | PDM | CSAM | CSA | Factory | ISD | Partner
1 — Qualify & Plan
1.1 | Identify Wave 1 candidate accounts | A | C | C | I | C | R | R | I | I | I
1.2 | Confirm AI Tech Ready signal & priority | R | A | C | I | I | C | C | I | I | I
1.3 | Single account plan (5-role v-team) | A | R | R | C | C | R | R | I | I | I
1.4 | Factory eligibility check (Unified Support / 2-page agreement) | I | C | I | I | C | A | R | C | I | I
1.5 | ISD model selection (A / B / C) | C | C | I | I | I | A | R | I | C | I
2 — Envision (Stage 1)
2.1 | Schedule envisioning workshop | A | C | C | I | I | R | R | I | I | C
2.2 | Deliver envisioning workshop | I | C | C | C | I | C | A·R | I | I | C
2.3 | Frontier 5+1 pillar governance assessment | I | C | I | I | I | C | A·R | I | I | I
2.4 | Three-surface mapping (M365 / Studio / Foundry) | I | C | C | C | I | C | A·R | I | I | C
3 — Assess (Stage 2)
3.1 | Solution Assessment claim (ATO Component 1 · pre-sale ECIF) | A | C | R | C | I | C | R | I | I | C
3.2 | Azure Innovate / AMM funding nomination | A | C | R | C | I | R | R | I | I | I
3.3 | Reference architecture & Responsible AI / POPIA review | I | A | C | R | I | C | R | C | C | C
3.4 | Business case & TCO | A | C | R | R | I | C | C | I | I | C
4 — Design & Build
4.1 | Factory nomination (F1 + F2 anchor bundle) | I | C | I | I | C | A | R | R | I | I
4.2 | F2 Azure Landing Zone delivery | I | I | I | I | I | I | C | A·R | I | I
4.3 | F1 GenAI Assistant MVP delivery | I | I | I | I | I | I | C | A·R | I | I
4.4 | Custom architecture & business logic beyond Factory | I | C | I | C | C | C | C | I | C | A·R
4.5 | Copilot Studio agent build | I | C | I | I | C | C | C | I | C | A·R
4.6 | M365 Copilot rollout & change management | I | C | C | I | C | C | C | I | I | A·R
4.7 | ISD-led sovereign / regulated delivery (Model B or C) | I | C | I | I | C | C | C | I | A·R | C
5 — Run & Scale (Stage 3+)
5.1 | ATO Component 2 (post-sale ECIF / ACO claim) | A | C | C | I | C | R | R | I | C | C
5.2 | MAU & adoption telemetry tracking | C | C | I | I | I | A·R | C | I | I | C
5.3 | Champions programme & user enablement | C | I | I | I | I | A | R | I | I | C
5.4 | Hand-off to managed services / steady-state | I | C | I | I | C | A | R | I | I | R
6 — Partner & Governance
6.1 | Anchor Partner scorecard & qualification | I | I | I | I | A·R | C | C | I | I | –
6.2 | Partner co-sell registration (MSX / IP Co-sell) | C | I | C | I | A·R | C | I | I | I | R
6.3 | Quarterly CoE governance review | C | C | I | I | C | A | R | C | C | C
6.4 | Customer reference / case study | A | C | C | I | C | R | R | C | C | C
6.5 | Renewal / E7 Frontier Firm step-up | A·R | C | R | C | C | C | C | I | I | I
Footnote — Partner column on row 4.7 (ISD-led delivery) applies to ISD Model C (ISD + ICSU + Partner) only. A · R indicates a single role that is both Accountable and Responsible.