AI Centre of Excellence · FY27 Launch Plan

MCAPS RSA · Area Leadership Brief · 1 July 2026 go-live

Owner: Yuri Baijnath · SR CSA Manager · MCAPS RSA CSU · Sponsors: GM RSA · Area CSU Leads (Cloud & AI · Modern Work · Business Applications) · Area ATU Lead · Area STU Lead · Area EPS Lead · Area ISD Lead

FY27 AMBITION

Stand up the AI Centre of Excellence motion as a repeatable, CSA-led, partner-delivered offering for MCAPS RSA — covering all three AI surfaces (M365 Copilot · Copilot Studio · Azure AI Foundry) under one operating model, executed through Microsoft's AI Transformation Offer (ATO) as the funded delivery engine, and accelerated by Cloud Accelerate Factory as the zero-cost CSU foundation layer (F1 GenAI Assistant + F2 Azure Landing Zone as the default Stage-2 anchor bundle). Convert AI enthusiasm into scaled Azure consumption, Copilot seats, Copilot Studio agents in production, and Fabric capacity at 6 flagship accounts in H1 and 12+ by year end — while qualifying the Anchor Partner ecosystem that sustains the motion beyond FY27. Benchmark: 100+ accounts already running ATO see 15% higher MoM AI ACR.

ALIGNMENT WITH AREA FY27 STRATEGY — AI AS A GROWTH ENGINE

The CoE motion is not a parallel initiative — it is the operating system that delivers six published Area FY27 objectives. Every Wave 1 engagement contributes to multiple targets simultaneously.

| Area FY27 objective | Area target | How CoE motion contributes |
| --- | --- | --- |
| Win the Socket / Chat | 500k active users · 80% target usage | Surface A entry point at every Wave 1 account. Envisioning workshops drive Copilot Chat 30% gate; Champions programme + Tips in 20 lift Apps/User to 2.5+. |
| Copilot Standalone (non-E7) | $10M · 400k paid seats · Lightning Bolt 80% coverage at 2000+ employees | CoE governance unblocks tenant config, Data Protection, Content Sharing — the gates that hold standalone deployments back at scale. |
| Frontier Firm E7 Bundle | $150M · 20 customers stepping up at renewal | Wave 1 Lighthouse cohort overlaps the renewal-to-E7 list. CoE evidence (production agents · MAU > 75% · governance ratified) is the proof that justifies the step-up. |
| Customer Agentic AI Journey | 300k MAU of agents · Copilot Studio $5M | Surface B is core to the CoE. Departmental Champs + Power Platform & Connectors path drives ID Agents → Build POC → OoB Agents 3 → Custom Agents. |
| AI Transformation of Strategic Apps | 1M DAU on Foundry/Apps · Top 17 ZA Consumer Apps (60M users) | Surface C — ATO Components 2 & 3 deliver landing zones, Custom Workflow, billing instrumentation. Cloud Accelerate Factory underwrites the F2 Azure Landing Zone at $0 to compress time-to-foundation. CoE underwrites Responsible AI for consumer-facing scale. |
| Government Alignment | Chat for every Civil Servant | Public sector lighthouse (City of Cape Town · Western Cape Government · SARS · SARB) anchored by ISD Model A or B given sovereignty profile. |

PRE-LAUNCH RUNWAY (NOW → 27 JUN 2026)

| Milestone | Action | Owner · Due |
| --- | --- | --- |
| M1 · Sponsorship | Secure named endorsement from GM RSA and the full MCAPS v-team leadership: Area CSU Leads (Cloud & AI · Modern Work · Business Applications), Area ATU Lead, Area STU Lead, Area EPS Lead, Area ISD Lead. Motion on Area FY27 plan. | Yuri · 9 May 2026 |
| M1b · Five-role v-team | Confirm named leads across ATU (account orchestration), STU (pursuit-level technical win — MW / BizApps / AI SSPs), CSU (three-surface delivery lead), EPS (PDM for partner lifecycle), ISD (optional Microsoft-led delivery). Single account plan per Wave 1 customer — not five parallel plans. | Yuri + Area Leads · 16 May 2026 |
| M2 · Wave 1 cohort | 6 flagship accounts selected from the AI Tech Ready H2/H3 list with named AE/SSP/CSA/PDM plus Modern Work + BizApps counterparts. Candidate pool: Standard Bank, ABSA, FirstRand, Nedbank, Capitec, Investec, Discovery, Old Mutual, Sanlam (financial services); MTN, Telkom, Naspers (TMT); Eskom, Sasol, AngloGold Ashanti (industrials); SARS, SARB, City of Cape Town, Western Cape Government (public sector). Target mix: 2 bankers, 2 stretch, 1 regulated, 1 public sector. Each account tagged with anchor surface (A, B, C, or A+B+C). | Yuri + ATU leads · 23 May 2026 |
| M3 · Anchor Partners | Scorecard applied to candidate list. 2–3 Anchors signed (MoU, co-sell hygiene, MAICPP status verified). EPS (PDM) primes partner lifecycle; CSU provides technical scoring support. | EPS + Yuri · 6 Jun 2026 |
| M3b · Factory engagement model | Confirm Factory eligibility per Wave 1 account (Unified Support OR signed 2-page Factory Agreement). Agree F1 GenAI Assistant + F2 Azure Landing Zone as the default Stage-2 anchor-bundle nomination across the cohort. Nominate Factory PM and align nomination cadence (~2 weeks lead-time) with ATO Component 2 kickoff dates. Brief Anchor Partners that Factory absorbs predictable foundation work — partner SOW shifts to differentiated build, not shrinks. | Yuri + CSU Factory PM · 10 Jun 2026 |
| M4 · CSA readiness | 2-day enablement on Playbook Sections 4, 5, 7, 12, 14, 15 (ATO), 16 (ISD option), plus Factory nomination workflow (F1/F2 anchor bundle, eligibility gates, partner-impact narrative). Dry-run Envisioning workshop with a friendly account; confirm ATO Component 1 delivery fluency across the team. | Yuri + CSU · 13 Jun 2026 |
| M4b · ISD engagement model | Align with Area CSU Lead + ISD leadership on the three delivery models (ISD-only · ISD+Partner · ISD+ICSU+Partner). Publish escalation path and model-selection criteria. Identify Wave 1 accounts (if any) that fit Model B or C. | Yuri + Area CSU + ISD · 20 Jun 2026 |
| M5 · Compliance gates | Legal, Responsible AI, POPIA sign-off on reference architecture (Section 12). Named reviewers per gate. | CSA + RAI + Legal · 20 Jun 2026 |
| M6 · Launch assets | Field note (1 page), partner summit deck, customer positioning talking points. All signed off. | Yuri · 27 Jun 2026 |

LAUNCH WAVES

| Wave | Timing | Audience | Channel |
| --- | --- | --- | --- |
| Internal | Week 1 · 6–10 Jul 2026 | MCAPS RSA field · ATU · STU · CSU · ISD · Partner team | Segment all-hands + Area leadership readout + 1-page field note |
| Partner | Week 2–3 · 13–24 Jul 2026 | Anchor Partners (live) · broader channel (email) | Half-day Anchor summit (in-person) · tier-appropriate channel comms |
| Customer | Week 4+ · from 27 Jul 2026 | Wave 1 cohort (account-by-account) | ATU-led; Envisioning workshop as entry point. No public launch in FY27 H1. |

90-DAY & FY27 METRICS

| Metric | Q1 target | H1 target | FY27 target |
| --- | --- | --- | --- |
| Wave 1 accounts in Stage 2 (Assess) | 6 | 6 | 12+ |
| Funded engagements claimed (Solution Assessment · Azure Innovate · AMM · ECIF) | 4 | 8 | 16+ |
| Anchor Partner co-sell registrations (MSX) | 6 | 15 | 30+ |
| Envisioning workshop NSAT | ≥ 8/10 | ≥ 8/10 | ≥ 8.5/10 |
| ACR lift per active CoE account (vs prior TTM) | Baseline | +15% | +30% |
| Published customer reference stories | 0 | 2 | 4+ |
| F2 Azure Landing Zone deployments nominated via Cloud Accelerate Factory | 2 | 4 | 8+ |
| F1 GenAI Assistant MVPs delivered via Cloud Accelerate Factory | 1 | 3 | 6+ |

TOP RISKS & MITIGATIONS

- Partner over-reach into Envision/Assess → CSA owns Stage 1–2; escalate same day to PDM if a partner pushes.

- Wave 1 account stalling (exec sponsor loss) → replace within 2 weeks; do not let a dead account clog the narrative.

- CSA fatigue by Q3 → two quarterly "CoE days" ring-fenced; public recognition of top deliverers at ALT.

- Framework fatigue in the field → every comms tethers CoE to an existing priority (Copilot, Fabric, Azure Innovate).

- Compliance bottleneck → named Legal/RAI/POPIA reviewers confirmed before launch; not discovered in Week 3.

- Factory eligibility gap → confirm Unified Support or signed 2-page Factory Agreement at qualification; otherwise predictable foundation work falls back into partner SOW or Microsoft-billed engagement and the $0 Stage-2 anchor bundle is lost.

THE ASK

(1) Endorse the motion on the FY27 Area plan. (2) Confirm GM RSA + Area CSU Lead + Area Partner Lead as named sponsors. (3) Authorise ring-fenced CSA capacity (2 CoE days per CSA per quarter). (4) Sponsor the Anchor Partner summit in July 2026. (5) Approve the H1 funding envelope for Solution Assessments, Azure Innovate, and AMM against the Wave 1 cohort.

DECISION REQUESTED

Approve FY27 launch as scoped, with a first-read of results at the January 2027 Area H1 review.